## SW TEST
Resource Name |  |  | Jude Fajardo and Lily Rose Julianes |  |  | PTP Review Date: | N/A |  |  | Total TCs |  | 25 |  | 1ST PASSED RATE | 2ND PASSED RATE | EXECUTION RATE | DEFECT RATE | REGRESSION PASSED RATE
Application Name |  |  | SafeGrounds |  |  | Sprint Review Date: | 2025-02-05 |  |  | Passed |  | 9 |  | 36% | 36% | 100% | 64% | 36%
Date Created |  |  | 2025-02-05 | [6 empty] | Failed |  | 16
[10 empty] | Not Applicable (NA) |  | 0
DATE | Test Case # | Sprint # | User Story # | User Stories | Persona | Scenarios | Impacted Modules | Test Cases | Expected Results/Acceptance Criteria | Test Execution Status |  |  | DEF/ENH No. | Tester | Execution Date | Closed Date | Remarks
[10 empty] | PASS 1 | PASS 2 | PASS 3
2025-02-09 | 1 | 1 | 1 | As a user I want to open a and use the features offered by the wbesite. | User | Using the Map | Map | GIVEN: I am in the main interface showing the map WHEN: I first access the website. | THEN: Verify that I can access the interface of the website | Passed | Passed | Passed |  | Quennie Magno and Joshua Ean Valera | 2025-02-09 | 2025-02-09 | Add more features and possibly create more navigation method and searching feature
[9 empty] | AND: Verify that I can see the website logo. | Passed | Passed | Passed
[9 empty] | AND: Verify that when I clicked "Show Evacuation Centers" the indicators were shown. | Passed | Passed | Passed
[9 empty] | AND: Verify that the zoom button is working. | Passed | Passed | Passed
[9 empty] | AND: Verify that the zoom out button is working. | Passed | Passed | Passed | 1
[9 empty] | AND: Verify that if I click the location indicator, It shows the name of the place. | Passed | Passed | Passed
[9 empty] | AND: Verify that when I clicked HOME button, it will return me to the main page. | Passed | Passed | Passed
[9 empty] | AND: Verify that I can navigate the map using my cursor. | Passed | Passed | Passed
2025-03-09 | 2 | 2 | 2 | As a user I want to find the shortest and safest path to the nearest evacuation center so that I can evaluate efficiently during a disaster. | User | Finding the Nearest Evacuation Center | Map | GIVEN: I am on the map interface WHEN: I select "Find Nearest Evacuation Center" | THEN: Verify that the system calculates and display the shortest route | Passed | Passed | Passed |  | Quennie Magno and Joshua Ean Valera | 2025-03-09 | 2025-03-09 | Improve the algorithm used
[9 empty] | AND: Verify that the system dynamically updates my location as I move | Failed | Failed | Failed
[9 empty] | AND: Verify that an Alternative route option is available if needed | Failed | Failed | Failed
[9 empty] | AND: Verify that the system handles large-scale mapping efficiently | Failed | Failed | Failed
[9 empty] | AND: Verify that an error message is displayed if no centers are nearby. | Failed | Failed | Failed
2025-03-09 | 3 | 2 | 3 | As the user, I want to see the details of evacuation centers so that I can choose the best option for my needs. | User | Viewing Evacuation Center Details | Map | GIVEN: I am on the map interface WHEN: I click on an evacuation center capacity,facilities, and contact info | AND: Verify that full evacuation centers are marked as "Full" or unavailable | Failed | Failed | Failed |  | Quennie Magno and Joshua Ean Valera | 2025-03-09 | 2025-03-09 | Improve the map interface
AND: Verify that the data updates when the center's status changes
[10 empty] | Failed | Failed | Failed
2025-03-09 | 4 | 2 | 4 | As the user, I want to Filter evacuation center based on the type of disaster so that I can find the safest option for my situation. | User | Filtering Evacuation Centers by Disaster Type | Map | GIVEN: I am using the filtering feature WHEN: I select a disaster type(e.g., Flood,Storm,Earthquake) | THEN: Verify that only evacuation centers safe from that disaster type are displayed | Failed | Failed | Failed |  | Quennie Magno and Joshua Ean Valera | 2025-03-09 | 2025-03-09 | Improve the Filter system to show properly the evacuations center
[9 empty] | AND: Verify that the filter updates dynamically when switching between disaster types | Failed | Failed | Failed
2025-03-09 | 6 | 2 | 5 | As the user, I want to receive clear error messages so that went wrong and how to fix it. | User | Handling Errors and Warnings | Map | GIVEN: My GPS is turned off WHEN: I try to search for evacuation centers GIVEN: I have no internet connection WHEN: I try to load the map GIVEN: I search for an evacuation center in an isolated location WHEN: No centers are found | THEN: Verify that the system notifies me to enable location services | Failed | Failed | Failed |  | Quennie Magno and Joshua Ean Valera | 2025-03-09 | 2025-03-09 | Improve error handling and show properly the error messages.
[9 empty] | THEN: Verify that an appropriate error message appers | Failed | Failed | Failed
[9 empty] | THEN: Verify that a message informs me that no centers are available nearbly | Failed | Failed | Failed
2025-03-09 | 7 | 2 | 6 | As an admin, I want to ensure user data is encrypted so that their personal information is secure. | Admin | Ensuring Data Privacy & Security | Map | GIVEN: A user shares their location WHEN: The system transmits data GIVEN: A user is unauthorized WHEN: They attempt to access restricted admin features | THEN: Verify that the location data is encrypted before transmission | Failed | Failed | Failed |  | Quennie Magno and Joshua Ean Valera | 2025-03-09 | 2025-03-09 | Improve the security of the system
[9 empty] | THEN: Verify that access is denied | Failed | Failed | Failed
2025-03-09 | 8 | 2 | 7 | As an user, I want the app to respond quickly so that I can get information during emergencies without delay. | User | Ensuring System Perfomance Under Load | Map | GIVEN: I request a rout to an evacuation center WHEN: The system process my request GIVEN: There are 1,000+ user online WHEN: The system is uncer high traffic | THEN: Verify that a result is turned within 5 seconds | Failed | Failed | Failed |  | Quennie Magno and Joshua Ean Valera | 2025-03-09 | 2025-03-09 | Possibly connect and subscribe to the updates by the Local Disaster Management Office
[9 empty] | THEN: Verify that app remains functional without crashing | Failed | Failed | Failed
2025-03-09 | 9 | 2 | 8 | As an user, I want to receive alerts about disaster so that I can take action immediately. | User | Receiving Disaster Alerts & Updates | Map | GIVEN: There is an incoming typhoon WHEN: The local disaster management office issues an alert GIVEN: The app is clossed WHEN: A critical alert is sent | THEN: Verify that the system notifies all users | Failed | Failed | Failed |  | Quennie Magno and Joshua Ean Valera | 2025-03-09 | 2025-03-09 | Improve the notifications system
[9 empty] | THEN: Verify that the user receives a push notification | Failed | Failed | Failed